## Slide 1
Project Risk Management
Kaustubh Gupta

## Slide 2
The Importance of Project Risk Management
Project risk management is the art and science of identifying, assigning, and responding to risk throughout the life of a project and in the best interests of meeting project objectives
Risk management is often overlooked on projects, but it can help improve project success by helping select good projects, determining project scope, and developing realistic estimates
KPMG study found that 55 percent of runaway projects did no risk management at all

## Slide 3
Project Risk Classification

## Slide 4
What is Risk?
A dictionary definition of risk is “the possibility of loss or injury”
Project risk involves understanding potential problems that might occur on the project and how they might impede project success
Risk management is like a form of insurance; it is an investment

## Slide 5
Risk Utility
Risk utility or risk tolerance is the amount of satisfaction or pleasure received from a potential payoff
  Utility rises at a decreasing rate for a person who is risk-averse
  Those who are risk-seeking have a higher tolerance for risk and their satisfaction increases when more payoff is at stake
  The risk neutral approach achieves a balance between risk and payoff

## Slide 6
Risk Utility Function and Risk Preference

## Slide 7
What is Project Risk Management?
The goal of project risk management is to minimize potential risks while maximizing potential opportunities. Major processes include
  Risk management planning: deciding how to approach and plan the risk management activities for the project
  Risk identification: determining which risks are likely to affect a project and documenting their characteristics
  Qualitative risk analysis: characterizing and analyzing risks and prioritizing their effects on project objectives
  Quantitative risk analysis: measuring the probability and consequences of risks

## Slide 8
  Risk response planning: taking steps to enhance opportunities and reduce threats to meeting project objectives
  Risk monitoring and control: monitoring known risks, identifying new risks, reducing risks, and evaluating the effectiveness of risk reduction

## Slide 9
The main output of risk management planning is a risk management plan
The project team should review project documents and understand the organization’s and the sponsor’s approach to risk
The level of detail will vary with the needs of the project
Risk Management Planning

## Slide 10
Questions Addressed in a Risk Management Plan

## Slide 11
Contingency and Fallback Plans, Contingency Reserves
Contingency plans are predefined actions that the project team will take if an identified risk event occurs
Fallback plans are developed for risks that have a high impact on meeting project objectives
Contingency reserve or allowances are provisions held by the project sponsor that can be used to mitigate cost or schedule risk if changes in scope or quality occur

## Slide 12: Other than Project Risk
Market risk: Will the new product be useful to the organization or marketable to others? Will users accept and use the product or service?
Financial risk: Can the organization afford to undertake the project? Is this project the best way to use the company’s financial resources?
Technology risk: Is the project technically feasible? Could the technology be obsolete before a useful product can be produced?

## Slide 13
Risk Identification
Risk identification is the process of understanding what potential unsatisfactory outcomes are associated with a particular project
Several risk identification tools and techniques include
  Brainstorming
  The Delphi technique
  Interviewing
  SWOT analysis

## Slide 14
Quantitative Risk Analysis
Assess the likelihood and impact of identified risks to determine their magnitude and priority
Risk quantification tools and techniques include
  Probability/Impact matrixes
  The Top 10 Risk Item Tracking technique
  Expert judgment

## Slide 15
Top 10 Risk Item Tracking
Top 10 Risk Item Tracking is a tool for maintaining an awareness of risk throughout the life of a project
Establish a periodic review of the top 10 project risk items
List the current ranking, previous ranking, number of times the risk appears on the list over a period of time, and a summary of progress made in resolving the risk item

## Slide 16
Example of Top 10 Risk Item Tracking

## Slide 17
Quantitative Risk Analysis
Often follows qualitative risk analysis, but both can be done together or separately
Large, complex project involving leading edge technologies often require extensive quantitative risk analysis
Main techniques include
  Decision tree analysis
  simulation

## Slide 18
Decision Trees and Expected Monetary Value (EMV)
A decision tree is a diagramming method used to help you select the best course of action in situations in which future outcomes are uncertain
EMV is a type of decision tree where you calculate the expected monetary value of a decision based on its risk event probability and monetary value

## Slide 19
Simulation
Simulation uses a representation or model of a system to analyze the expected behavior or performance of the system
Monte Carlo analysis simulates a model’s outcome many time to provide a statistical distribution of the calculated results
To use a Monte Carlo simulation, you must have three estimates (most likely, pessimistic, and optimistic) plus an estimate of the likelihood of the estimate being between the optimistic and most likely values

## Slide 20
Risk Response Planning
After identifying and quantifying risk, you must decide how to respond to them
Four main strategies:
  Risk avoidance: eliminating a specific threat or risk, usually by eliminating its causes
  Risk acceptance: accepting the consequences should a risk occur
  Risk transference: shifting the consequence of a risk and responsibility for its management to a third party
  Risk mitigation: reducing the impact of a risk event by reducing the probability of its occurrence

## Slide 21
General Risk Mitigation Strategies for Technical, Cost, and Schedule Risks

## Slide 22: Risk Monitoring and Control
Monitoring risks involves knowing their status
Controlling risks involves carrying out the risk management plans as risks occur
Workarounds are unplanned responses to risk events that must be done when there are no contingency plans
The main outputs of risk monitoring and control are corrective action, project change requests, and updates to other plans

## Slide 23
Risk Response Control
Risk response control involves executing the risk management processes and the risk management plan to respond to risk events
Risks must be monitored based on defined milestones and decisions made regarding risks and mitigation strategies
Sometimes workarounds or unplanned responses to risk events are needed when there are no contingency plans

## Slide 24
Results of Good Project Risk Management
Unlike crisis management, good project risk management often goes unnoticed
Well-run projects appear to be almost effortless, but a lot of work goes into running a project well
Project managers should strive to make their jobs look easy to reflect the results of well-run projects

## Slide 25
THANK YOU